## Sheet1
Interface | Trader Interface - PHP
Test Area | Feature | Expected Result | Result
Register | Register as a new trader | Trader registration form is displayed | PASS
| Register with invalid details | Access to registration denied | PASS
| Register with valid details | Registration process is successful and verified | PASS
| E-mail Verification | Trader is verified via e-mail | PASS
Login | Trader login with valid details | Trader is successfully logged in after admin approval | PASS
| Trader login with invalid details | Access denied | PASS
Trader Rights | Add trader type | Trader type is added and awaits approval from the admin | PASS
| Traders can add shop | Shop is added for the trader | PASS
| Add new products | Trader can add new products | PASS
| Update existing product details | Trader can update details of existing product | PASS
| Delete existing product | Trader can delete product | PASS
| Logout | Login Page is displayed | PASS
| View Profile | Trader can view their profile | PASS
| Update Profile | Trader can edit their profile | PASS
Interface | Trader Interface - Oracle APEX
Test Area | Feature | Expected Result | Result
Login | Trader login with valid details | Trader is successfully logged in after admin approval | PASS
| Trader login with invalid details | Access denied | PASS
Trader Rights | View Dashboard | Traders can view dashboard with summary | PASS
| View Order Details | Traders can view a report of orders for the day with required information | PASS
| View Product Report | Trader can view shop, products and their details | PASS
| View Stocks Report | Trader can view and update stocks with this report | PASS
| View product reviews | Traders can view products review made by the customers | PASS
| Sales Report | Trader can see all the sales report | PASS
| Product Sales Report | Trader can see Total Orders Per Product, Total Income Per Product of products which can be sorted as required | PASS